## Slide 1: YAM Project Updates
Madhukar Trivedi, MD
Center for Depression Research and Clinical Care
UT Southwestern Medical Center

## Slide 2: YAM Train-the-Facilitator Sessions: HRI’s Represented
March 2022
TTUHSC
UTSA
UTSW
July 2022
TAMU
Dell
UT Tyler
UTSW
July 2022
TTUHSC
Dell
UT Houston
UTSA
UTSW

## Slide 3: YAM Train-the-Facilitator Sessions: HRI’s Represented
August 2022
UTSA
UTMB
UTSW
UT Houston
Sept 2022
TAMU
TTUHSC
UT Houston
UTSA
UT Tyler
UTSW
Oct 2022
TAMU
Dell
TTUHSC
UT Houston
UTSA
UT Tyler
UTSW

## Slide 4: Progress: 125 Instructors Trained
Next Training Scheduled in December

## Slide 5: Schools / Districts Engaged by HRIs
Dell
UTMB
Dickinson ISD
UTHSC Houston
Humble ISD
Pro-Vision Academy*
TAMU
TTUHSC
UTHSC San Antonio
UTHC Tyler
UTSW
Copperas Cove ISD
Dripping Springs ISD
Hays CISD
Wayside Schools
Fruitvale ISD*
Hawkins ISD
Winnsboro ISD
Friendswood ISD
Hitchcock ISD
Arlington ISD*
Beeville ISD
Bonham ISD
Ector ISD
Trenton ISD
Uplift Charter Network*
Eula ISD*
Houston ISD
Bronte ISD*
Irion County ISD
Santa Anna ISD*
Gunter ISD*
Plano ISD*
Harlandale ISD
San Antonio ISD
Boerne ISD
East Central ISD
Huntsville ISD
Killeen ISD
HEB ISD*
Arp ISD*
Vega ISD*
Santa Anna ISD*
Milano ISD
Buna ISD
College Station ISD
Bryan ISD
Elysian Fields ISD
Harper ISD
George West ISD
Poteet ISD
Aldine ISD
Pasadena ISD
Pearland ISD
Harmony Public Schools
Fort Bend ISD
Katy ISD
* = YAM already delivered / currently being delivered

## Slide 6: YAM Student Reach
Spring 2022
1,800
Sept 2022
300
Oct 2022
900
Currently delivering YAM to ~1500 students
Projected Total Reach
at end of Nov 2022
5,000

## Slide 7: YAM Student Classes
Spring 2022
98
Sept. 2022
22
Oct. 2022
38
Currently delivering YAM in ~75 classes
Projected Total Classes
at end of Nov 2022
~300

## Slide 8: Sneak Peak – Depression Data Measures
Chart: PHQ-2: Little interest or pleasure in doing things
| Nearly everyday | More than half of days | Several days | Not at all
Pre (N = 227) | 19 | 35 | 79 | 94
Post (N = 232) | 14 | 37 | 68 | 113
Chart: PHQ-2: Feeling down, depressed or hopeless
| Nearly everyday | More than half of days | Several days | Not at all
Pre (N = 227) | 15 | 16 | 64 | 132
Post (N = 232) | 12 | 23 | 54 | 143
Prior to YAM implementation - 25.8% of students scored ≥ 3 on PHQ-2

## Slide 9: Sneak Peak – Anxiety Data Measures
Chart: GAD-2: Feeling nervous, anxious or on edge
| Nearly everyday | More than half of days | Several days | Not at all
Pre (N = 225) | 20 | 33 | 77 | 95
Post (N = 232) | 21 | 37 | 63 | 111
Chart: GAD-2: Not being able to stop or control worrying
| Nearly everyday | More than half of days | Several days | Not at all
Pre (N = 226) | 17 | 24 | 70 | 115
Post (N = 232) | 14 | 34 | 52 | 132
Prior to YAM implementation – 26.4% of students scored ≥ 3 on GAD-2